## Sheet1
Date | People involved |  | Topic | Priority |  | Details | Decision | Deadline
| from Company | from Customer |  | Company | Customer |  |  | Days | Date
2016-09-11 | Project manager | Accountant | Data migration | High | Urgent | AP and AR data not imported properly | wait until month end | 20 | 2016-10-01 | Low | Software
2016-09-11 | Project manager | Project manager | Software | Medium | High | confusion about cost of licenses | ask sales | 1 | 2016-09-12 | Medium | Implementation
2016-09-11 | Consultant | Project manager | Implementation | Low | Medium | customer not available for phase 2 | postpone one week | 7 | 2016-09-18 | High | Consulting
2016-09-11 | Sales | Project manager | Software | High | Low | possible upsale for licenses | customer decided not to buy more for now | na | na | Urgent | Data migration
Formulas:
Date = [Date]+[Deadline]